## general_report
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Fix Version/s | Component/s | Due Date | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Detected in Version | Personal data (GDPR) | Storypoints | Test documentation | Development | Global Rank (Obsolete) | Reproducible | Area Impact | Category Customer | Affected Components | Sprint | Epic Link | What has been changed | Epic Name | Reason for Change | Coding Authorised Date | Committed | Original Storypoints | Estimated Test Hours | Component and Function Area | Sprint team | Last Financial Update | Coding Authorised By | Log Path | Budget Label | Customer | Budget Referance | Customer group | Tested By | QC_Reference | Request Date | Responsible Architect | Defect owner | Assignment | Category Project | Release documentation | Category Team | Category Assignee | ALM Test ID | Epic/Theme | Required Doc | Assigned To | JCS Share Issue | Main Branch | Rank (Obsolete) | Retested By | Dev Branch Tester | Ranking (Obsolete) | Test activities | Customer ranking (Obsolete) | Hotfix approved by | MyTime Info | Responsible Tester | Revenue sum(NOK) | Approved By | Project number cascading | Business Value | Customer reference | Target start | Parent Link | Build approved by | Original story points | Responsible BA | Rank | Target end | Customer ranking | Retest Versjonsnr | Global Rank | Team | Ranking | Terp Codes | Environment type | Flagged | Story Points | Epic Status | Change type | Epic Colour
Test Automation | TESTAUT-990 | Test Automation Analysis: Corporate Action Events | Epic | Awaiting info | Major | Unresolved | Shahare Vaibhav | Hildegunn Espedal | Hildegunn Espedal | 2014.01.24 21:39:18 | 2024.09.08 12:04:29 | 2024.09.02 14:37:11 |  | ToBeDecided | Corporate Actions |  | 1 |  |  | 0 | 18000 |  |  | TESTAUT-1412, TESTAUT-2248 |  | Analyze and suggest scenarios to automate for the Corporate Action module in ProBroker. The analysis should result in a suggested list of test cases that will cover the module. Implementation will be handled in new issues; one for each test case. Creation of CA event for different type of CA types. 1. Creation and execution of *Dividend* CA type. a. Dividend CA is two types i. Dividend payed in cash. ii. Dividend payed in form of shares. i.Create CA event for dividend payed in cash after executing verify two dialog Portfolio and account ledger. ii.Create CA event for dividend payed in shares after executing verify dialog Portfolio. iii.Verify CA dividend when client setup under the restriction dialog. (working of dividend restriction dialog -> client having the restriction then dividend will be updated under the dividend holder client.) 2. *Refund* (value of a portfolio will be paid as a cash amount). i.Create position for the instrument and create the CA event Refund for the same instrument. ii.Run the CA and then verify the portfolio and ledger iii.Trade price should be updated under the portfolio for the instrument. iv.Ledger entry for the instrument and client should be updated under the account ledger dialog. 3. *Redemption* (This CA-type has the ability to run an exercise where you replace the positions with a given amount per number) i.Create position for the instrument and create the CA event Redemption for the same instrument. ii.Portfolio and ledger should be updated as per the instruction provided under the CA event. iii.Ledger should be updated with tax and redemption amount. Redemption of unused subscription rights 1. CA-event ‘Redemption’ to clear the portfolio 2. Amount per share is not required in this case 3. Portfolio will then be 0 in stock and it will not generate any gains / losses. Here one can see that there has been a manual portfolio transaction with ‘IL’ code and inventory becomes zero. 4. *Merger* (Two or more companies merge into a company) i.Create position for the instrument and create the CA event Merger for the same instrument. ii.Portfolio should be updated as per the instruction provided under the CA event. 5. *Demerger* (divide a company into two or more units) i. Create position for the instrument and create the CA event Demerger for the same instrument. ii. Only portfolio should be updated as per the CA event created. no Ledger entry is posted for this CA. 6. *Split* (used to increase the number of shares in a corporation) i. Only portfolio is updated when we execute the Split CA.(Split - increases the no. of shares in portfolio 1-10) ii. Reverse Split - decreases the no. of shares 10-1 7. *Bonus Issue* :: Increase of share capital through a bonus share issue can be made by transfer to share capital from share premium fund and from the free reserves and without payment from the shareholder. 1. Only portfolio (Position) is updated when we execute Bonus Issue. 2. No transaction created in ledger. (TESTAUT-3521) 8. *Convert* :: One instrument is converted into another instrument.Portfolio will be moved from the old instrument to the new 1. Portfolio (Position) is updated when we execute the convert CA. All position of old(from)instrument is conevrted to new(To) instrument. 2. No transaction created in ledger. 3. Unsettled transactions in the old instrument will not be moved over to the new instrument. (TESTAUT-3522) 9. *Rights distribution* :: Issue receives often existing shareholders a preferential right to purchase new shares in the company (warrants). This means that for every share you own, you receive x number of warrants,often at a fixed price . 1. Portfolio (position) is changed for the right distribution instrument when we execute Right distribution CA as per the ration given in CA. event. 2. No change in the ledger. (TESTAUT-3523) 10. *Tender Offer* :: Offers a cash payment or payment in the form of shares in another company. 1. Portfolio is updated when user run the tender offer CA. 2. Ledger entry is also posted once the CA event is successfully executed. 3. Position for From instrument ( for which CA event is created) is updated in portfolio when Acquisition is approved. (TESTAUT-3525) 11. *Bond term* :: For handling redemption and interest payments for bonds. 1. CA event is only for Bond type of instrument.(1. Pool instrument, non pool instrument) 2. Portfolio is updated for once the CA event is executed. 3. Ledger entry is also posted when CA event is executed. (TESTAUT-1338) 12. *Right Execution* :: CA event used to redeem the shares(Warrants). 1. Portfolio is updated for both the instrument( Position for right instrument is reduced to zero and one MPT entry is displayed for the right execution instrument with quantity as 0 and price as 0) 2. One ledger entry is also created for the right execution instrument. (TESTAUT-3524) |  | 100% | 100% | 18000 | 0 |  |  | 99 |  |  |  |  | 35238 | [7 empty] | CorporateActionEvents | [5 empty] | Corporate Actions - Corporate Action Events | Test Automation |  |  |  |  | Internal | [8 empty] | AnalysisTestAutomation | [9 empty] | 44775 |  |  | 34045 |  | 47849 | [13 empty] | 2¦hz9x91:w |  | 0¦i087cn: |  | 0¦i061ev: |  | 0¦i05ufn: | Project: 139366 ProBroker Release 2013, Task: Test Automation
Test Automation | TESTAUT-580 | Test Automation Analysis: Billing | Epic | Awaiting info | Major | Unresolved | Shahare Vaibhav | Hildegunn Espedal | Hildegunn Espedal | 2012.07.04 15:49:46 |  | 2023.09.07 12:07:24 |  | ToBeDecided | Billing |  | 1 | [6 empty] | PBINT-9892, TESTAUT-1405, TESTAUT-675, TESTAUT-676, TESTAUT-677, TESTAUT-678, TESTAUT-679, TESTAUT-680, TESTAUT-681, TESTAUT-687, TESTAUT-1399, PBINT-7224, TESTAUT-689, TESTAUT-694, TESTAUT-695 |  | Analyze and suggest scenarios to automate for the Billing module in ProBroker. The analysis should result in a suggested list of test cases that will cover the module. Implementation will be handled in new issues; one for each test case. Billing module is being re-written under PBINT-7224; Need to add new test scripts and adjust existing (subsequently remove obsolete test scripts), once rewrite is complete. Need to analyze what kind of test cases that are needed for the Billing area together with the testers in Daredevils. The analysis should result in one "Test Automation" enhancement issue for each new test case, and one "Test Case Update" enhancement issue for each existing test case that needs adjustments. ~~ We have modified 'BillingServicesDiscounts' under TESTUAT-1399, although there are existing application issues, which are being fixed under PBINT-15273 & PBINT-15274 - we need to analyze this test case again once PBINT-7224 is finalized and conclude on how the final version of this test case should be. 20160303 - Vaibhav have created an excel with suggested flows - need to look into which of these that is suitable for automation: "I:\Department\PD\Test\ProBroker\Test Case In Progress\20160303 Test Scenarios - billing service.xlsx" "I:\Department\PD\Test\ProBroker\Test Case In Progress\Test scenarios for billing_001.xlsx" Consider following while designing scenarios: 1. Add service fee under client maintenance tab for daily, weekly, monthly, quarterly, half yearly, yearly and verify the next batch date for the same and verify different status on fee monitor/edit client dialog . 2. For daily service fee we can automate to verify the amount on payment, account overview dialogs and manual and BBS settlement for service fee. 3. For monthly, quarterly service fee create the service fee with different parameters and add under the client maintenance dialog and verify the status and next batch date. 4. Above scenarios can be created for different client setup with cash holding, without cash holding, reservation with bank client, reservation with ledger client, with cash account without cash account. 5. Scenarios with the discount, special price. 6. Cancellation of service fee before settlement, after settlement. Input from Mari-Ann related to billing rewrite: BILLING - Regular service fee - Depot fee (with and without minimum amount, with and without depot/portfolio, different combinations of batch parameters clearing_agent and clearing_central) - Recurring fee - Not recurring fee - Recurring for a number of periods - Renewal 1st day in period (Days for renewal = 0 or 1 or NULL) - Renewal on specific day in period, middle of period (Days for renewal = 2 to 26) - Renewal on specific day in period, end of period (Days for renewal = 27 or above) - Registration on day for renewal - Registration after day for renewal - Registration before day for renewal (future fee) How service fee is registered or renewed has to be tested for each type of fee (fee period) - Daily - Weekly - Monthly * - Quarterly * - Half yearly - Yearly We should prioritize testing monthly and quarterly fees as this is most commonly used. Yearly fee will be rewritten, so have to test this as well now. - Snapshot - With payments (Nets, Evry) - Without payments - With cash account (Nets, Evry) - Without cash account (setting decides if registering fee without cash account is allowed) - With cash account without payment (NONE) - Regular clients - Cash holdings client - With VAT - Without VAT - With discount (with and without discount group) - Without discounts - With special price - Without special price - With coverage control (with bank reservation, without bank reservation = coverage control against ledger, client has coverage, client has not coverage) - Without coverage control - Handling of rejected fees and how to trigger them for renewal (if reservation is rejected, if payment fails etc) - Connection between customer categories and fees, which is also used to trigger fee registration in relation to new agreements on the client. - Client with settlement NOK, fee in NOK - Client with settlement NOK, fee in <>NOK - Client with settlement <>NOK, fee in NOK - Client with settlement <>NOK, fee in <>NOK - Client with settlement blank, fee in NOK - Client with settlement blank, fee in <>NOK - Fee with agreed currency rate - Override order source when registering new client service fee (to see that balance control is used for correct order source) - Reports/Dispatches - Batches (65 Kansellere utgåtte tjenester, 48 Fornyelse av kundetjenester) - Settings (ALWAYS_RENEW, IGNORE_DEPOTFEE_IF_NO_POSITION, IGNORE_MISSING_CASH_ACCOUNT, others?) - Authorizations - We should also keep in mind/document how the accounting setup should be for service fee/vat Important actions: - Registration/New - Change (Change Client Service Fee, Edit Service Fee) - Cancellation (before settlement, after settlement, of client service fee, of service fee, of fee voucher) - Settlement (manual, different payment agents (Evry, Nets)) - Renewal - Stop (will be introduced later) Important to verify every time (what to verify depends on what is done, for example there might be different verifications for new client service fee and renewal. Sometimes general verifications for account overview has to be done, sometimes other dialogs will be important): - Amounts - Statuses - Dates - Cash account Important dialogs involved in Billing-testing: - Edit Client, Services tab - New Client Service - Service Fees - New Service fee - Service Fee Types - New Service Fee Type - Depot Commission - VAT Rules - Fee Monitor (should be called Service Fee Overview) - Account overview - Payments - Reservations - Portfolio (foreign instruments) - Manual settlement - Voucher Registration | [12 empty] | 20248 | [7 empty] | Billing | [5 empty] | Billing | Test Automation |  |  |  |  | Internal | [8 empty] | AnalysisTestAutomation | [9 empty] | 21163 |  |  | 34119 |  | 36635 | [13 empty] | 2¦hz9x7p: |  | 0¦i06a4n: |  | 0¦i03gvr: |  | 0¦i05tbo:
Test Automation | TESTAUT-1697 | Test Automation: Payments NETS Change Trans CancelSentPayments1 | Enhancement Request | New | Major | Unresolved | Unassigned | Hildegunn Espedal | Hildegunn Espedal | 2015.11.25 13:47:22 |  | 2022.01.26 17:42:59 |  | ToBeDecided | Payment & Reservations |  | 0 |  | 216000 | 216000 |  | 0% |  | TESTAUT-1003, TESTAUT-1696 |  | Test case to cover change transaction scenarios for payment agent NETS after generating file to NETS, when system setting ORDRSRVR CancelSentPayments = 1. Test case covers both scenario for Net transaction and ordinary transaction. Preconditions: Clients with Cash Account for Payment Agent NETS: ClientDirectDebit (1): Direct Debit ClientCounterpart (5): No cash account/payments setup - use this client as counterpart in all the contract notes System Setting BBSSRVR->SETTTLEMENT_ACC_NO = 0 ORDRSRVR->CANCEL_SENT_PAYMENTS = 1 Important ProBroker services: BBSSrvr.exe The basic flow includes the following: Change System Setting: Change system setting ORDRSRVR CANCEL_SENT_PAYMENTS from 0 to 1 (default value in the test automation system should be 0). Restart related services. Scenario 1: Create Payment: Register one buy and one sale contract note on client using default NETS Cash Account setup, where buy amount is larger than sale amount, so multiple payment transactions appear in Settlement - Payment - Payments. Net: Open Settlement - Payments - Generate Payment File, check "Net - settlement", Credit and Debit, press Search. The transactions will be netted, so you get one line per cash account. Create File: Activate the ones you are not going to send to NETS now. Press Generate File to send the desired transactions to NETS (file is generated on a folder defined in BBSSrvr.ini). Change Transaction: Change the buy and the sale contract note. Change commission on buy contract note and price on sale contract note. (Warning or Not Allowed? - transactions will not be changed) Read File (Clean Up): File is received on a folder that BBS Server polls on (defined in BBSSrvr.ini - for testing you need to take the generated file, "manually" move it to the folder and rename it to *.kdk). BBS server process the file and settle and update status on the payment transactions. Create all the transactions you need for the scenario before generating the file: Scenario for Change Net Transactions: Create Payment - Net- Create File - Change Transaction - Read File: 1. AGR > KRD - Contract Notes - Client 1 End Scenario 1. Start Scenario 2: Create Payment: Register one buy and one sale contract note on client using default NETS Cash Account setup, so multiple payment transactions appear in Settlement - Payment - Payments. Create File: Open Settlement - Payments - Generate Payment File, check Credit and Debit, press Search. One line will appear per transaction. Activate the ones you are not going to send to NETS now. Press Generate File to send the desired transactions to NETS (file is generated on a folder defined in BBSSrvr.ini). Change Transaction: Change the buy and the sale contract note. Change commission on buy contract note and price on sale contract note. (Warning or Not Allowed? - transactions will not be changed) Read File (Clean Up): File is received on a folder that BBS Server polls on (defined in BBSSrvr.ini - for testing you need to take the generated file, "manually" move it to the folder and rename it to *.kdk). BBS server process the file and settle and update status on the payment transactions. Create all the transactions you need for the scenario before generating the file: Scenario for Change Transactions: Create Payment - Create File - Change Transaction - Read File: 1. AGR Contract Note - Client 1 2. KRD Contract Note - Client 1 End Scenario 2. Change System Setting (Clean Up): Change system setting ORDRSRVR CANCEL_SENT_PAYMENTS back to 0. Restart related services. For each action there will be different things that needs to be verified in different dialogs such as Manual Settlement dialog, Payments dialog, Account Overview (ledger) dialog etc. Call existing test cases, like Manual Contract Notes, Contract Note Change etc. as far as possible. Create new action test cases for repeatable actions if applicable (discuss the need with PO). I:\ProBroker\Dokumentasjon\Systemdokumentasjon (intern)\Reservation and Payments\Settle status Flow.xlsx gives an overview of the expected statuses after each action performed. |  | 0% | 0% |  | 216000 | 216000 | [6 empty] | 9.2234e+18 | No |  |  |  |  | Payments | [7 empty] | Payments & Reservations - NETS | Test Automation |  |  |  |  | Internal | [8 empty] | Test Automation | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [13 empty] | 2¦hz87of: |  | 0¦i0azgn: |  | 0¦i0ayw7: |  | 0¦i0az9z: | Project: 139366 ProBroker Release, Task: Test Automation
Test Automation | TESTAUT-4697 | PaymentsNETSSplitSendPartManStlmntCancelReadV: Implement payments and ledger action test cases | Enhancement Request | New | Medium | Unresolved | Unassigned | Swapnali Mankar | Swapnali Mankar | 2022.05.24 11:06:10 |  | 2024.08.02 14:27:56 |  |  |  |  | 1 |  | 644400 | 644400 |  | 0% |  | TESTAUT-4573 |  | PaymentsNETSSplitSendPartManStlmntCancelReadV Implement the following action test cases: In TESTAUT-4514 action test case *AccountOverviewLedgerSearch* for searching in Account Overview ledger dialog was created. In TESTAUT-4515 *AccountOverviewLedgerVerification* was improved. In TESTAUT-4516 action test case *SettlementStatusesBankVerification* for verifying Settlement Statuses Bank dialog from Account Overview or Payments dialog was created. In TESTAUT-4067 *PaymentsSearch* action test case for searching for payments on Payments dialog was created. In TESTAUT-4068 *PaymentsVerification* action test case for verifying payments on Payments dialog will be created. |  | 0% | 0% |  | 644400 | 644400 |  | 99.0.0.0.0 |  |  |  |  | 9.2234e+18 |  |  |  |  | 202413 Test Automation | Payments | [7 empty] | Payments & Reservations - Payment Management | Test Automation |  |  |  |  | Internal | [8 empty] | TestCaseUpdate | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [7 empty] | 2¦hz80bw:4y00014c |  | 0¦i0v7fr: |  | 0¦i0v3wz: |  | 0¦i0v78n:
Test Automation | TESTAUT-4704 | PaymentsNETSSplitSendReadCancelV: Implement payments and ledger action test cases | Enhancement Request | New | Medium | Unresolved | Unassigned | Swapnali Mankar | Swapnali Mankar | 2022.05.24 11:11:51 |  | 2024.08.02 14:27:56 |  |  |  |  | 1 |  | 421200 | 421200 |  | 0% |  | TESTAUT-4573 |  | PaymentsNETSSplitSendReadCancelV Implement the following action test cases: In TESTAUT-4514 action test case *AccountOverviewLedgerSearch* for searching in Account Overview ledger dialog was created. In TESTAUT-4515 *AccountOverviewLedgerVerification* was improved. In TESTAUT-4516 action test case *SettlementStatusesBankVerification* for verifying Settlement Statuses Bank dialog from Account Overview or Payments dialog was created. In TESTAUT-4067 *PaymentsSearch* action test case for searching for payments on Payments dialog was created. In TESTAUT-4068 *PaymentsVerification* action test case for verifying payments on Payments dialog will be created. |  | 0% | 0% |  | 421200 | 421200 |  | 99.0.0.0.0 |  |  |  |  | 9.2234e+18 |  |  |  |  | 202413 Test Automation | Payments | [7 empty] | Payments & Reservations - Payment Management | Test Automation |  |  |  |  | Internal | [8 empty] | TestCaseUpdate | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [7 empty] | 2¦hz80bw:4y000146 |  | 0¦i0v7hb: |  | 0¦i0v3yj: |  | 0¦i0v7a7:
Test Automation | TESTAUT-4703 | PaymentsNETSSplitSendReadFullManStlmntCancelCN: Implement payments and ledger action test cases | Enhancement Request | New | Medium | Unresolved | Unassigned | Swapnali Mankar | Swapnali Mankar | 2022.05.24 11:11:06 |  | 2024.08.02 14:27:56 |  |  |  |  | 1 |  | 345600 | 345600 |  | 0% |  | TESTAUT-4573 |  | PaymentsNETSSplitSendReadFullManStlmntCancelCN Implement the following action test cases: In TESTAUT-4514 action test case *AccountOverviewLedgerSearch* for searching in Account Overview ledger dialog was created. In TESTAUT-4515 *AccountOverviewLedgerVerification* was improved. In TESTAUT-4516 action test case *SettlementStatusesBankVerification* for verifying Settlement Statuses Bank dialog from Account Overview or Payments dialog was created. In TESTAUT-4067 *PaymentsSearch* action test case for searching for payments on Payments dialog was created. In TESTAUT-4068 *PaymentsVerification* action test case for verifying payments on Payments dialog will be created. |  | 0% | 0% |  | 345600 | 345600 |  | 99.0.0.0.0 |  |  |  |  | 9.2234e+18 |  |  |  |  | 202413 Test Automation | Payments | [7 empty] | Payments & Reservations - Payment Management | Test Automation |  |  |  |  | Internal | [8 empty] | TestCaseUpdate | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [7 empty] | 2¦hz80bw:4y00014 |  | 0¦i0v7h3: |  | 0¦i0v3yb: |  | 0¦i0v79z:
Test Automation | TESTAUT-4706 | PaymentsNETSSplitSendReadPartManStlmntCancelV: Implement payments and ledger action test cases | Enhancement Request | New | Medium | Unresolved | Unassigned | Swapnali Mankar | Swapnali Mankar | 2022.05.24 11:13:03 |  | 2024.08.02 14:27:56 |  |  |  |  | 1 |  | 345600 | 345600 |  | 0% |  | TESTAUT-4573 |  | PaymentsNETSSplitSendReadPartManStlmntCancelV Implement the following action test cases: In TESTAUT-4514 action test case *AccountOverviewLedgerSearch* for searching in Account Overview ledger dialog was created. In TESTAUT-4515 *AccountOverviewLedgerVerification* was improved. In TESTAUT-4516 action test case *SettlementStatusesBankVerification* for verifying Settlement Statuses Bank dialog from Account Overview or Payments dialog was created. In TESTAUT-4067 *PaymentsSearch* action test case for searching for payments on Payments dialog was created. In TESTAUT-4068 *PaymentsVerification* action test case for verifying payments on Payments dialog will be created. |  | 0% | 0% |  | 345600 | 345600 |  | 99.0.0.0.0 |  |  |  |  | 9.2234e+18 |  |  |  |  | 202413 Test Automation | Payments | [7 empty] | Payments & Reservations - Payment Management | Test Automation |  |  |  |  | Internal | [8 empty] | TestCaseUpdate | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [7 empty] | 2¦hz80bw:4y00013u |  | 0¦i0v7hr: |  | 0¦i0v3yz: |  | 0¦i0v7an:
Test Automation | TESTAUT-4705 | PaymentsNETSSplitSendReadPartManStlmntCancelCN: Implement payments and ledger action test cases | Enhancement Request | New | Medium | Unresolved | Unassigned | Swapnali Mankar | Swapnali Mankar | 2022.05.24 11:12:28 |  | 2024.08.02 14:27:56 |  |  |  |  | 1 |  | 324000 | 324000 |  | 0% |  | TESTAUT-4573 |  | PaymentsNETSSplitSendReadPartManStlmntCancelCN Implement the following action test cases: In TESTAUT-4514 action test case *AccountOverviewLedgerSearch* for searching in Account Overview ledger dialog was created. In TESTAUT-4515 *AccountOverviewLedgerVerification* was improved. In TESTAUT-4516 action test case *SettlementStatusesBankVerification* for verifying Settlement Statuses Bank dialog from Account Overview or Payments dialog was created. In TESTAUT-4067 *PaymentsSearch* action test case for searching for payments on Payments dialog was created. In TESTAUT-4068 *PaymentsVerification* action test case for verifying payments on Payments dialog will be created. |  | 0% | 0% |  | 324000 | 324000 |  | 99.0.0.0.0 |  |  |  |  | 9.2234e+18 |  |  |  |  | 202413 Test Automation | Payments | [7 empty] | Payments & Reservations - Payment Management | Test Automation |  |  |  |  | Internal | [8 empty] | TestCaseUpdate | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [7 empty] | 2¦hz80bw:4y00013o |  | 0¦i0v7hj: |  | 0¦i0v3yr: |  | 0¦i0v7af:
Test Automation | TESTAUT-4702 | PaymentsNETSSplitSendReadFullManStlmntCancelV: Implement payments and ledger action test cases | Enhancement Request | New | Medium | Unresolved | Unassigned | Swapnali Mankar | Swapnali Mankar | 2022.05.24 11:10:12 |  | 2024.08.02 14:27:55 |  |  |  |  | 1 |  | 324000 | 324000 |  | 0% |  | TESTAUT-4573 |  | PaymentsNETSSplitSendReadFullManStlmntCancelV Implement the following action test cases: In TESTAUT-4514 action test case *AccountOverviewLedgerSearch* for searching in Account Overview ledger dialog was created. In TESTAUT-4515 *AccountOverviewLedgerVerification* was improved. In TESTAUT-4516 action test case *SettlementStatusesBankVerification* for verifying Settlement Statuses Bank dialog from Account Overview or Payments dialog was created. In TESTAUT-4067 *PaymentsSearch* action test case for searching for payments on Payments dialog was created. In TESTAUT-4068 *PaymentsVerification* action test case for verifying payments on Payments dialog will be created. |  | 0% | 0% |  | 324000 | 324000 |  | 99.0.0.0.0 |  |  |  |  | 9.2234e+18 |  |  |  |  | 202413 Test Automation | Payments | [7 empty] | Payments & Reservations - Payment Management | Test Automation |  |  |  |  | Internal | [8 empty] | TestCaseUpdate | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [7 empty] | 2¦hz80bw:4y00013i |  | 0¦i0v7gv: |  | 0¦i0v3y3: |  | 0¦i0v79r:
Test Automation | TESTAUT-4707 | PaymentsNETSSplitSendReadPartMStlFullMStlCancelCN: Implement payments and ledger action test cases | Enhancement Request | New | Medium | Unresolved | Unassigned | Swapnali Mankar | Swapnali Mankar | 2022.05.24 11:13:35 |  | 2024.08.02 14:27:54 |  |  |  |  | 1 |  | 259200 | 259200 |  | 0% |  | TESTAUT-4573 |  | PaymentsNETSSplitSendReadPartMStlFullMStlCancelCN Implement the following action test cases: In TESTAUT-4514 action test case *AccountOverviewLedgerSearch* for searching in Account Overview ledger dialog was created. In TESTAUT-4515 *AccountOverviewLedgerVerification* was improved. In TESTAUT-4516 action test case *SettlementStatusesBankVerification* for verifying Settlement Statuses Bank dialog from Account Overview or Payments dialog was created. In TESTAUT-4067 *PaymentsSearch* action test case for searching for payments on Payments dialog was created. In TESTAUT-4068 *PaymentsVerification* action test case for verifying payments on Payments dialog will be created. |  | 0% | 0% |  | 259200 | 259200 |  | 99.0.0.0.0 |  |  |  |  | 9.2234e+18 |  |  |  |  | 202413 Test Automation | Payments | [7 empty] | Payments & Reservations - Payment Management | Test Automation |  |  |  |  | Internal | [8 empty] | TestCaseUpdate | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [7 empty] | 2¦hz80bw:4y00010o |  | 0¦i0v7hz: |  | 0¦i0v3z7: |  | 0¦i0v7av:
Test Automation | TESTAUT-5331 | CorporateActionBondTerm: Implement ledger action test cases | Enhancement Request | New | Medium | Unresolved | Unassigned | Deepali Chavan | Deepali Chavan | 2024.02.01 18:06:44 |  | 2024.08.02 14:27:54 |  |  |  |  | 2 |  | 162000 | 162000 |  | 0% |  | TESTAUT-4573, TESTAUT-5311 |  | CorporateActionBondTerm Implement the following action test cases: In TESTAUT-4514 action test case *AccountOverviewLedgerSearch* for searching in Account Overview ledger dialog was created. In TESTAUT-4515 *AccountOverviewLedgerVerification* was improved. Consider TESTAUT-5311 suggestion for the Account Overview dialog where we can provide the date to filter out the other back dated entries to reduce time for verification. |  | 0% | 0% |  | 162000 | 162000 |  | 99.0.0.0.0 |  |  |  |  | 9.2234e+18 |  |  |  |  | 202413 Test Automation | Ledger Account Overview & Voucher | [7 empty] | Corporate Actions - Corporate Action Events | Test Automation |  |  |  |  | Internal | [8 empty] | TestCaseUpdate | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [7 empty] | 2¦hz80bw:4y000106 |  | 0¦i100zb: |  | 0¦i0zwzf: |  | 0¦i100s7:
Test Automation | TESTAUT-4699 | PaymentsNETSSplitSendPartManStlmntReadCancelV: Implement payments and ledger action test cases | Enhancement Request | New | Medium | Unresolved | Unassigned | Swapnali Mankar | Swapnali Mankar | 2022.05.24 11:08:08 |  | 2024.08.02 14:27:53 |  |  |  |  | 1 |  | 403200 | 403200 |  | 0% |  | TESTAUT-4573 |  | ManualSettlementInternalSettlementScenarios Implement the following action test cases: In TESTAUT-4514 action test case *AccountOverviewLedgerSearch* for searching in Account Overview ledger dialog was created. In TESTAUT-4515 *AccountOverviewLedgerVerification* was improved. In TESTAUT-4516 action test case *SettlementStatusesBankVerification* for verifying Settlement Statuses Bank dialog from Account Overview or Payments dialog was created. In TESTAUT-4067 *PaymentsSearch* action test case for searching for payments on Payments dialog was created. In TESTAUT-4068 *PaymentsVerification* action test case for verifying payments on Payments dialog will be created. |  | 0% | 0% |  | 403200 | 403200 |  | 99.0.0.0.0 |  |  |  |  | 9.2234e+18 |  |  |  |  | 202413 Test Automation | Payments | [7 empty] | Payments & Reservations - Payment Management | Test Automation |  |  |  |  | Internal | [8 empty] | TestCaseUpdate | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [7 empty] | 2¦hz80bw:4y0000h |  | 0¦i0v7g7: |  | 0¦i0v3xf: |  | 0¦i0v793:
Test Automation | TESTAUT-4695 | PaymentsNETSSplitSendFullManStlmntCancelReadV: Implement payments and ledger action test cases | Enhancement Request | New | Medium | Unresolved | Unassigned | Swapnali Mankar | Swapnali Mankar | 2022.05.24 11:05:01 |  | 2024.08.02 14:27:52 |  |  |  |  | 1 |  | 622800 | 622800 |  | 0% |  | TESTAUT-4573 |  | PaymentsNETSSplitSendFullManStlmntCancelReadV Implement the following action test cases: In TESTAUT-4514 action test case *AccountOverviewLedgerSearch* for searching in Account Overview ledger dialog was created. In TESTAUT-4515 *AccountOverviewLedgerVerification* was improved. In TESTAUT-4516 action test case *SettlementStatusesBankVerification* for verifying Settlement Statuses Bank dialog from Account Overview or Payments dialog was created. In TESTAUT-4067 *PaymentsSearch* action test case for searching for payments on Payments dialog was created. In TESTAUT-4068 *PaymentsVerification* action test case for verifying payments on Payments dialog will be created. |  | 0% | 0% |  | 622800 | 622800 |  | 99.0.0.0.0 |  |  |  |  | 9.2234e+18 |  |  |  |  | 202413 Test Automation | Payments | [7 empty] | Payments & Reservations - Payment Management | Test Automation |  |  |  |  | Internal | [8 empty] | TestCaseUpdate | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [7 empty] | 2¦hz80bw:4y0000g |  | 0¦i0v7fb: |  | 0¦i0v3wj: |  | 0¦i0v787:
Test Automation | TESTAUT-4698 | PaymentsNETSSplitSendPartManStlmntReadCancelCN: Implement payments and ledger action test cases | Enhancement Request | New | Medium | Unresolved | Unassigned | Swapnali Mankar | Swapnali Mankar | 2022.05.24 11:07:31 |  | 2024.08.02 14:27:52 |  |  |  |  | 1 |  | 396000 | 396000 |  | 0% |  | TESTAUT-4573 |  | PaymentsNETSSplitSendPartManStlmntReadCancelCN Implement the following action test cases: In TESTAUT-4514 action test case *AccountOverviewLedgerSearch* for searching in Account Overview ledger dialog was created. In TESTAUT-4515 *AccountOverviewLedgerVerification* was improved. In TESTAUT-4516 action test case *SettlementStatusesBankVerification* for verifying Settlement Statuses Bank dialog from Account Overview or Payments dialog was created. In TESTAUT-4067 *PaymentsSearch* action test case for searching for payments on Payments dialog was created. In TESTAUT-4068 *PaymentsVerification* action test case for verifying payments on Payments dialog will be created. |  | 0% | 0% |  | 396000 | 396000 |  | 99.0.0.0.0 |  |  |  |  | 9.2234e+18 |  |  |  |  | 202413 Test Automation | Payments | [7 empty] | Payments & Reservations - Payment Management | Test Automation |  |  |  |  | Internal | [8 empty] | TestCaseUpdate | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [7 empty] | 2¦hz80bw:4y0000f |  | 0¦i0v7fz: |  | 0¦i0v3x7: |  | 0¦i0v78v:
Test Automation | TESTAUT-4694 | PaymentsNETSSplitSendFullManStlmntCancelReadCN: Implement payments and ledger action test cases | Enhancement Request | New | Medium | Unresolved | Rupesh Sure | Swapnali Mankar | Swapnali Mankar | 2022.05.24 11:04:19 |  | 2024.08.01 13:57:04 |  |  |  |  | 2 |  | 622800 | 622800 |  | 0% |  | TESTAUT-4573 |  | PaymentsNETSSplitSendFullManStlmntCancelReadCN Implement the following action test cases: In TESTAUT-4514 action test case *AccountOverviewLedgerSearch* for searching in Account Overview ledger dialog was created. In TESTAUT-4515 *AccountOverviewLedgerVerification* was improved. In TESTAUT-4516 action test case *SettlementStatusesBankVerification* for verifying Settlement Statuses Bank dialog from Account Overview or Payments dialog was created. In TESTAUT-4067 *PaymentsSearch* action test case for searching for payments on Payments dialog was created. In TESTAUT-4068 *PaymentsVerification* action test case for verifying payments on Payments dialog will be created. |  | 0% | 0% |  | 622800 | 622800 |  | 99.0.0.0.0 |  |  |  |  | 9.2234e+18 |  |  |  |  | 202413 Test Automation | Payments | [7 empty] | Payments & Reservations - Payment Management | Test Automation |  |  |  |  | Internal | [8 empty] | TestCaseUpdate | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [7 empty] | 2¦hz80bw:4y0000c |  | 0¦i0v7f3: |  | 0¦i0v3wb: |  | 0¦i0v77z:
Test Automation | TESTAUT-3525 | Test Automation: Corporate Action Tender Offer | Enhancement Request | New | Medium | Unresolved | Unassigned | Hildegunn Espedal | Hildegunn Espedal | 2019.12.09 18:10:43 |  | 2024.08.01 13:56:33 |  |  |  |  | 1 |  | 72000 | 72000 |  | 0% |  | TESTAUT-3524 |  | Create a scenario test case to cover flows for the corporate action type Tender Offer. Test case name: "*CorporateActionTenderOffer*" *Tender Offer:* Offers a cash payment or payment in the form of shares in another company. 1. The portfolio is updated when user run the tender offer CA. 2. Ledger entry is also posted once the CA event is successfully executed. 3. Position for From instrument (for which CA event is created) is updated in portfolio when Acquisition is approved. *Scenarios to cover:* Note:: tender offer A event is not working on an official test system will try to find out the problem and if required will create the PBINT for the same. 1. Verify the portfolio is updated for the "tender offer instrument" and "instrument from" as per the ratio provided in CA event. 2. Verify the ledger entry is created for the client as per the amount /per share amount provided in CA event (amt/share*quantity of the "instrument from" for the client) 3. Verify the book value is an update for the instrument. 4. verify if user rejected the offer on edit ca event dialog. 5. Cancel the CA event. |  | 0% | 0% |  | 72000 | 72000 | [6 empty] | 9.2234e+18 | No |  |  |  | 202415 Test Automation | CorporateActionEvents | [7 empty] | Corporate Actions - Corporate Action Events | Test Automation |  |  |  |  | Internal | [8 empty] | Test Automation | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [6 empty] | Shahare Vaibhav | 2¦hzyjet: |  | 0¦i0p2k7: |  | 0¦i0ozn7: |  | 0¦i0p2d3:
Test Automation | TESTAUT-3524 | Test Automation: Corporate Action Rights Execution | Enhancement Request | New | Medium | Unresolved | Unassigned | Hildegunn Espedal | Hildegunn Espedal | 2019.12.09 18:10:09 |  | 2024.08.01 13:56:33 |  |  |  |  | 1 |  | 72000 | 72000 |  | 0% |  | TESTAUT-3525 |  | Create a scenario test case to cover flows for the corporate action type Rights Execution. Test case name: "*CorporateActionRightsExecution*" *Right Execution:* CA event used to redeem the shares (Warrants). 1. Portfolio is updated for both the instrument (Position for right instrument is reduced to zero and one MPT entry is displayed for the right execution instrument with quantity as 0 and price as 0) 2. One ledger entry is also created for the right execution instrument. *Scenarios to cover:* 1. Verify ledger entry and portfolio for the client when the user overrides the number of allotted shared and no. of wanted shares. Ledger entry should be cerated - issue price * no shares wanted. portfolio for the right instrument gets reduced by no. shares wanted. Portfolio for right execution instrument increased by no. shares wanted. 2. Verify ledger entry and client entry when the user rejected the right execution offer from edit basis. NOTE:: On official test system now Manual restriction transaction is cerated when CA is executed, so need to check this behaviour. 3. Cancel CA event and verify ledger and MPT both entries get canclled. |  | 0% | 0% |  | 72000 | 72000 | [6 empty] | 9.2234e+18 | No |  |  |  | 202415 Test Automation | CorporateActionEvents | [7 empty] | Corporate Actions - Corporate Action Events | Test Automation |  |  |  |  | Internal | [8 empty] | Test Automation | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [6 empty] | Shahare Vaibhav | 2¦hzyjes: |  | 0¦i0p2jz: |  | 0¦i0ozmz: |  | 0¦i0p2cv:
Test Automation | TESTAUT-3523 | Test Automation: Corporate Action Rights Distribution | Enhancement Request | New | Medium | Unresolved | Unassigned | Hildegunn Espedal | Hildegunn Espedal | 2019.12.09 18:09:15 |  | 2024.08.01 13:56:33 |  |  |  |  | 1 |  | 72000 | 72000 |  | 0% |  |  |  | Create a scenario test case to cover flows for the corporate action type Rights Distribution. Test case name: "*CorporateActionRightsDistribution*" *Rights distribution:* Issue receives often existing shareholders a preferential right to purchase new shares in the company (warrants). This means that for every share you own, you receive x number of warrants, often at a fixed price. 1. Portfolio (position) is changed for the right distribution instrument when we execute right distribution CA as per the ration given in CA event. 2. No change in the ledger. *Scenarios to cover:* Verify portfolio for the right distribution instrument - Position/ holding for the instrument as per the ration is given in CA event. MPT should be created with the price 0. No changes on the ledger for the client. NO changes on a portfolio for the Instrument. 2. Canel the CA event and verify portfolio is back to original. |  | 0% | 0% |  | 72000 | 72000 | [6 empty] | 9.2234e+18 | No |  |  |  | 202415 Test Automation | CorporateActionEvents | [7 empty] | Corporate Actions - Corporate Action Events | Test Automation |  |  |  |  | Internal | [8 empty] | Test Automation | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [6 empty] | Shahare Vaibhav | 2¦hzyjer: |  | 0¦i0p2jj: |  | 0¦i0ozmj: |  | 0¦i0p2cf:
Test Automation | TESTAUT-3522 | Test Automation: Corporate Action Convert | Enhancement Request | New | Medium | Unresolved | Unassigned | Hildegunn Espedal | Hildegunn Espedal | 2019.12.09 18:08:13 |  | 2024.08.01 13:56:33 |  |  |  |  | 1 |  | 72000 | 72000 |  | 0% |  |  |  | Create a scenario test case to cover flows for the corporate action type Convert. Test case name: "*CorporateActionConvert*" *Convert:* One instrument is converted into another instrument.Portfolio will be moved from the old instrument to the new 1. Portfolio (Position) is updated when we execute the convert CA. All position of old(from)instrument is converted to new(To) instrument. 2. No transaction created in the ledger. 3. Unsettled transactions in the old instrument will not be moved over to the new instrument. *Scenarios to cover:* Verify if user provides fraction instrument then MPT is cerated for fraction instrument as well. Example: if a client having 80 positions and user provides the ratio as 3:1 then 78 positions to "instrument to" and reaming 2 positions updated in fraction instrument. Price calculation for MPT =Orginal postion = 80 ratio : 3:1 26*3 = 78 so 26 postion is added for "instrument to" and reaming postion is added for fraction instrument. consider book value as 800 so instrument rate as 10 so for fraction instrument MPT is created with quantity as 2 and price as 10. for "Instrument to" 780/26 = 30 MPT is cerated with price as 30 and quantity as 26. 2. Canel the CA event and verify portfolio is back to original. |  | 0% | 0% |  | 72000 | 72000 | [6 empty] | 9.2234e+18 | No |  |  |  | 202415 Test Automation | CorporateActionEvents | [7 empty] | Corporate Actions - Corporate Action Events | Test Automation |  |  |  |  | Internal | [8 empty] | Test Automation | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [6 empty] | Shahare Vaibhav | 2¦hzyjeq:i |  | 0¦i0p2jb: |  | 0¦i0ozmb: |  | 0¦i0p2c7:
Test Automation | TESTAUT-3521 | Test Automation: Corporate Action Bonus Issue | Enhancement Request | New | Medium | Unresolved | Unassigned | Hildegunn Espedal | Hildegunn Espedal | 2019.12.09 18:05:48 |  | 2024.08.01 13:56:33 |  |  |  |  | 1 |  | 72000 | 72000 |  | 0% |  |  |  | Create a scenario test case to cover flows for the corporate action type Bonus Issue. Test case name: "*CorporateActionBonusIssue*" *Bonus Issue:* Increase of share capital through a bonus share issue can be made by transfer to share capital from share premium fund and from the free reserves and without payment from the shareholder. 1. Only portfolio (Position) is updated when we execute Bonus Issue. 2. No transaction created in ledger. *Scenarios to cover:* 1. Verify MPT is cerated for the both the instrument. 2. Verify position for instrument from is not changed after CA execution. 3. Verify position for Instrument to is updated as per the ratio provided in CA event. 4. Verify the Book value, instrument rate for the "instrument from" is updated as per the ratio. 5. Verify book value, instrument rate for the "instrument to" is also updated as per the ratio. 6. Verify MPT is created with the instrument rate displayed for "instrument from" for both instruments. 7. Cancel CA event - position is reverted as original. Example:: If the instrument from having position 100 and book value as 1000 If instrument to having position 50 and book value as 500. Ratio is 2: 1 provided in CA event. for Instrument from book value is updated as 666.67= (1000/150) and instrument rate as 6.67 for the instrument to book value is updated as 833.5= ((50*6.6)+500)/100) and instrument rate is 8.35 |  | 0% | 0% |  | 72000 | 72000 | [6 empty] | 9.2234e+18 | No |  |  |  | 202415 Test Automation | CorporateActionEvents | [7 empty] | Corporate Actions - Corporate Action Events | Test Automation |  |  |  |  | Internal | [8 empty] | Test Automation | [9 empty] | 9.2234e+18 |  |  | 9.2234e+18 |  | 9.2234e+18 | [5 empty] | ProBroker Release:245963 - Test Automation | [6 empty] | Shahare Vaibhav | 2¦hzyjeq: |  | 0¦i0p2j3: |  | 0¦i0ozm3: |  | 0¦i0p2bz:
Generated at Sun Sep 08 08:35:10 CEST 2024 by Swapnil Daphal using Jira 9.4.21#940021-sha1:84e26b3d1a2d938c65e3cb0346c67a8c198675a9.